## Sheet1
Stories | Task | Expected Time | Risk | Actual Time | % Complete | Code Review
As an engineer, I will be able to view the error log | Error Log is Viewable | 2 hours | 2 | 1 hour | 100% | Ken
As an engineer, I will be able to see the output of the tests | Tests print output | 1 hour | 2 | 40 minutes | 100% | Nick